## Sheet1
NOTIFICATION BREAKDOWN - BE
NO | FEATURE | BREAKDOWN | DESKRIPSI | FIBONACCI
1 | master parameter - sender | api for sender_config (insert,get all(list), get by id) | table, controller, entity, service, mapper | 3
|  | api for sender_config (delete, edit) | controller, service, mapper | 2
2 | Compose email and email history/mailing list | configuration | all config for mailing | 3
|  | send email | controller, entity | 3
|  | api for email history (insert, get all(list), get by id) | table, controller, entity, service, mapper | 3
|  | pagination |  | 3
3 | master parameter - email template category | api for email template category (insert, get all(list), get by id) | controller, entity, service, mapper | 3
|  | api for email template category (delete, edit) |  | 2
4 | email template | api for email template (insert,get all(list), get by id) - ngereference dari email template recipient | controller, entity, service, mapper | 3
|  | api for email template (delete, edit) - ngereference dari email template recipient | controller, entity, service, mapper | 3
|  | pagination |  | 3
dibagian insert : return id email template untuk preview template
5 | Send email with template | send email with template | controller, service | 3
|  | save sent email to email history/mailing list | controller, service, mapper | 3
37
NOTIFICATION BREAKDOWN - FE
NO | FEATURE | BREAKDOWN | DESKRIPSI | FIBONACCI
1 | Compose Email | tampilan compose email dengan field : recipient list (combo box), recipient (to, cc, bcc), subject, body, button send and cancel | form, controller, model, event pada button, routing, plugin : tinymce, validation | 3
2 | Email Sender | tampilan list email sender dengan struktur tabel berupa : No, Category, Description, Status, Action (Edit, Delete), add email sender, pagination, filter(sort) | controller, model, event pada button, routing, pagination, filtering(sort) | 2
|  | Action Edit : menampilkan form edit untuk mengubah template email | form, controller, model, routing, event pada button, validation | 2
|  | Add email sender | form, controller, model, routing, event pada button, validation | 2
3 | Email Template | tampilan list email template dengan struktur tabel berupa : No, Name, Category, Subject, Application, Tenant Type, Action (View dan Edit), add email template, pagination dan filter(sort) | controller, model, event pada button, routing, pagination, filtering(sort) | 2
|  | Add email template (field : recipient list (combo box), recipient (to, cc, bcc), subject, body, button submit and cancel) | form, controller, model, event pada button, routing, plugin : tinymce, validation | 3
|  | Action View : menampilkan preview dari body email | controller, model, routing, event pada button | 1
|  | Action Edit : menampilkan form edit untuk mengubah template email | form, controller, model, routing, event pada button, validation | 2
4 | Email Template Category | tampilan list kategori template email dengan struktur tabel berupa : No, Category, Description, Status, Action (Edit, Delete), add email template category, pagination dan filter(sort) | controller, model, routing, event pada button, pagination dan filtering(sort) | 2
|  | Action Edit : menampilkan form edit untuk mengubah template email category | form, controller, model, routing, event pada button, validation | 2
|  | Add email template category (field berupa : Category, Description, button submit and cancel) | form, controller, model, routing, event pada button, validation | 2
5 | History List | tampilan list history pengiriman pesan, button view (detail email), pagination dan filter(sort) | controller, pagination, event pada button dan filter(sort) | 2
25